# SCRUM MANAGEMENT

## Group 11

| Name | Email | ID |
| --- | --- | --- |
| Aya Mohamed | Aya.mohamed@e.braude.ac.il | 213914054 |
| Asad Rezek | Assad.Rezek@e.braude.ac.il | 212868962 |
| Ashrf Asadi | Ashrf.Asadi@e.braude.ac.il | 2124075582 |
| Marian Sayegh | Marian.Sayegh@e.braude.ac.il | 324005024 |
| Nora Abood | Nora.Abood@e.braude.ac.il | 324930312 |

Due Date: 7/12/2025

## This document explains how Group 11 uses the Scrum approach to manage and complete the project. Scrum is an agile method that helps teams handle complicated work by breaking it into small, repeatable steps.

## Roles & Responsibilities

## Product Owner: Ashraf Asadi
The Product Owner is responsible for:

### Arranging and ranking backlog items according to project priorities.

### Working with stakeholders to collect and clarify their needs.

### Communicating the product vision and plan to both the team and stakeholders.

### Choosing which features and tasks will be developed in each sprint.

### Checking finished backlog items to confirm they satisfy the required criteria.

Scrum Master: Asad Rezeq
The Scrum Master’s responsibilities include:

- Leading Scrum meetings and supporting the team in following Scrum practices.

- Removing blockers to keep the team moving forward.

- Encouraging effective teamwork and communication between members and stakeholders.

- Making sure the team stays focused on sprint goals and delivers meaningful results.

customers.
- Mentoring the team on Agile principles and Scrum practices.

# Sprint backlog

# Week 1

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Preparing to do list | Asad | 2.00 hours | ✅ Done |
| Project Setup & Scrum Initialization | All | 2.00 hours | ✅ Done |
| Requirements Analysis | Marian , Nora , aya | 1.5 hours | ✅ Done |
| Brainstorm system actors & roles | Asad, aya ,ashraf | 2.00 hours | ✅ Done |
| Sprint Planning | Marian , Nora, Asad | 1.00 hour | ✅ Done |

# Week 2

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Use Case Diagram | Aya , asad , ashraf | 5.00 hours | ✅ Done |
| Acceptance Test Design | Marian, nora | 3.00 hours | ✅ Done |
| Sprint Review and Submission assignment 1 | All | 2.00 hours | ✅ Done |

# Week 3

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Assignment 2 setup | All |  | ✅ Done |
| Build the Table Reservation diagram | Ashraf,aya,asad | 3.00 hours | ✅ Done |
| Build the Subscription Report activity diagram | Marian,nora | 3.00 hours | ✅ Done |

# Week 4

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Double-check that all use cases are covered | All | 0.50 hours | ✅ Done |
| Fix and refine Use Case Diagram based on team feedback | Ashraf,aya,Asad | 2.00 hours | ✅ Done |
| Polish flow of events texts to match diagram accurately | marian,Nora | 1.00 hours | ✅ Done |
| Confirm all ZIP files meet instructions and sumbiting assinment on Moodle | Ashraf | 0.50 hours | ✅ Done |

# Week 4

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Software Structure Description | Asad, ashraf, aya | 6.00 hoors | ✅ Done |
| integrate OCSF | Nora ,marian ,ashraf | 5.50 hours | ✅ Done |
| Apply design pattern | all | 6.00 hours | ✅ Done |

# Week 5

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| creating Table Reservation Sequence | Asad, ashraf, aya | 6.00 hours | ✅ Done |
| creating Cancel Reservation Sequence | Asad, ashraf, aya | 6.00 hours | ✅ Done |
| creating Table Receiving Sequence | Marian, nora | 5.00 hour | ✅ Done |
| creating Payment Sequence | Asad, ashraf, aya | 1.5 hour | ✅ Done |
| Create the Package Diagram in Visual Paradigm with all dependencies | Marian, nora | 2.00 hours | ✅ Done |

# Week 6

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Database Setup | Ashraf ,aya ,asad | 2.5 hours | ✅ Done |
| Building Server Prototype | Aya,ashraf,asad | 10.00 hours | ✅ Done |
| Building Client Prototype | Aya,ashraf,asad | 12.00 hours | ✅ Done |
| Final Testing & Documentation | All | 8.00 hours | ✅ Done |
| Submission assignment 2 | All | 1.00 hours | ✅ Done |

# WBS  Table

| Task ID | Task Name | Description | Start day | End day | Dependencies | Team Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Week 1 | 1 | Preparing to do list | Create a clear plan outlining tasks, order, and priorities to complete the project efficiently. | Day 1 | Day1 | --- | Asad |
|  | 2 | Project Setup & Scrum Initialization | Create Git repository, set up Scrum board, assign roles (Scrum Master, Product Owner, Developers) | Day 1 | Day 2 | — | All |
|  | 3 | Requirements Analysis | Gather and document system requirements (functional & non-functional), prepare SRS document | Day 3 | Day 4 | Task 1 | Marian , Nora , aya |
|  | 4 | Brainstorm system actors & roles | Discuss about the story to build the system and the actors | Day 4 | Day 5 | Task 2 | Asad, aya ,ashraf |
|  | 5 | Sprint Planning | Create detailed task list for Sprint 1, define deadlines and responsibilities | Day 5 | Day 5 | Task 1 | Marian , Nora, Asad |
| Week 2 | 6 | Use Case Diagram | Identify actors and use cases, draw the use case diagram, and describe each case | Day 1 | Day 3 | Task 4 | Aya , asad , ashraf |
|  | 7 | Acceptance Test Design | Define acceptance criteria and test scenarios to validate main features | Day 2 | Day 3 | Tasks 6 | Marian, nora |
|  | 8 | Sprint Review and Submission assignment 1 | Review Sprint 1 progress, update ToDo list | Day 4 | Day 5 | Tasks 7 | All |
| Week 3 | 9 | Assignment 2 setup | Understanding assignment 2 and assign roles | Day 1 | Day 2 | Task 8 | All |
|  | 10 | Build the Table Reservation diagram | Create a diagram showing how users reserve, cancel, and pay for a table. | Day 3 | Day 5 | Task 9 | Aya , ashraf, Asad |
|  | 11 | Build the Subscription Report activity diagram | Design a diagram showing how users create and view subscription reports. | Day 3 | Day 5 | Task 9 | Nora , marian |
| Week 4 | 12 | Software Structure Description | Define the system’s ECB layers, list main classes with key methods, and outline the overall package structure | Day 1 | Day 2 | Tasks 10, 11 | Asad, ashraf, aya |
|  | 13 | integrate OCSF | Show how client/server classes connect | Day 3 | Day 4 | Tasks 12 | Nora ,marian ,ashraf |
|  | 14 | Creating the final UML class diagramCreating the final UML class diagram | Produce complete UML class diagram with attributes, methods, relationships, patterns. | Day 4 | Day 5 | Tasks 13 | all |

| Week5 | 15 | Sequence diagrams preparation | Read assignment section, list 4 flows and main lifelines (GUI, controllers, entities, server, DB). | Day1 | Day1 | Task 14 | Asad, Ashraf ,aya |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 16 | Sequence diagram – Table reservation | Model the table reservation flow and draw the sequence diagram in VP. | Day1 | Day1 | Task15 | Asad, Ashraf ,aya |
|  | 17 | Sequence diagram – Cancel reservation | Model cancel reservation scenario and draw the sequence diagram. | Day2 | Day2 | Task 15 | Asad, Ashraf ,aya |
|  | 18 | Sequence diagram – Table receiving | Model table receiving when the customer arrives and draw the sequence diagram. | Day3 | Day3 | Task 15 | Marian, nora |
|  | 19 | Sequence diagram – Payment | Model payment after the meal and draw the sequence diagram. | Day 4 | Day 4 | Task 15 | Asad , ashraf, aya |
|  | 20 | Sequence diagrams review & export | Check consistency with activity/class diagrams, English names, then export all 4 diagrams. | Day5 | Day5 | Task 16, 17, 18 , 19 | all |
|  | 21 | Package diagram creation & review | Create the Package Diagram in VP, review dependencies, ensure ECB + pattern, export diagram. | Day6 | Day6 | Task 14 | Marian nora |
| Week 6 | 18 | Prototype DB setup | Choose main table, create it in DB, add sample data, test JDBC connection. | Day1 | Day1 | Task13 | Ashraf Asad aya |
|  | 19 | Server prototype – write/read operations | Implement server connection to DB and at least one read query; test from a small client. Add at least one write operation (insert/update) on the same table. | Day2 | Day 2 | Task 18 | Aya,ashraf,asad |
|  | 20 | Client prototype – read/write scenario & multi-client | Implement simple client UI to connect to server and display read results; build client JAR. Add write option from client, run at least two clients with same server and DB. | Day 3 | Day3 | Task18 | Aya,ashraf,asad |
|  | 21 | Prototype final testing & documentation | Full end-to-end tests, fix bugs, and write short “how to run prototype” instructions | Day4 | Day6 | Task18,19,20 | All |